## Sheet1
View Project | Region | Project Title | Project Reference | Agency Short Name | Sub Agency Short Name | Tender Board Type | Contract Value | Contractor(s) | Project End Date | Project Status | Completion Percent | Has Images
30068 | 04 | Construction of GWI Corporate Complex - Region 4 | GWIXXX202603X30068 | MOPUA | GWI | NPTAB |  |  | 2026-04-30 | DELAYED | 75 | 0
28281 | 01 | Supply and Delivery of Fiberglass Poles and Crossarms to the Hinterland Location. | HECIXX202602X28281 | MOPUA | HECI | NPTAB | $161,086,467 | SPR Enterprises | 2026-02-28 | DELAYED | 44 | 0
27696 | 04 | Supply of Transmission & Distribution Materials (Conductors). | GPLXXX202601X27696 | MOPUA | GPL | NPTAB | $606,365,198 | FIX-IT Depot |  | DELAYED | 0 | 0
27587 | 04 | Supply & Installation of In-Line Baggage Handling System | CJIAXX202601X27587 | MOPUA | CJIA | NPTAB | $512,300,000 | Total Solutions Inc. | 2024-01-20 | DELAYED | 80 | 6
27593 | 05 | Supply and installation of in line filters in Regions 2,4 and 5 | GWIXXX202601X27593 | MOPUA | GWI | NPTAB | $296,608,602 | Compass Industrial Services | 2025-12-01 | DELAYED | 95 | 8
27530 | 05 | Design supply and commissioning of Fifteen In line filters for GWI - Lot 4 | GWIXXX202601X27530 | MOPUA | GWI | NPTAB | $228,015,843 | International Imports and Supplies | 2024-09-29 | DELAYED | 92 | 5
27541 | 07 | Phase 2: Extension of Ekereku Bottom Airstrip | HASXXX202601X27541 | MOPUA | HAS |  |  |  | 2026-06-27 | DELAYED | 1 | 3
27539 | 07 | Rehabilitation of Kaikan Airstrip, Region 7 | HASXXX202601X27539 | MOPUA | HAS |  |  |  | 2026-09-30 | DELAYED | 1 | 0
27535 | 04 | Construction of New Administrative Building at the Cheddi Jagan International Airport | CJIAXX202601X27535 | MOPUA | CJIA | NPTAB | $890,440,820 | Avinash Contracting & Scrap Metal Inc | 2024-04-23 | DELAYED | 87 | 104
27534 | 06 | Design, supply and commissioning of fifteen in line filters Lot 2 (Crabwood Creek, #69, Johanna and Mibicuri Region 6) | GWIXXX202601X27534 | MOPUA | GWI | NPTAB | $266,564,347 | International Imports and Supplies | 2024-06-06 | DELAYED | 90 | 1
27532 | 01 | Rehabilitation of Matthew's Ridge Airstrip, Region 1 | HASXXX202601X27532 | MOPUA | HAS | NPTAB | $89,290,200,<br><br>$985,498,500,<br><br>$246,702,000 | GV Construction Inc.,<br><br>GV Construction Inc.,<br><br>Gafsons Industries Limited | 2026-01-31 | DELAYED | 55 | 25
27531 | 10 | Rehabilitation of Kwakwani Airstrip, Region 10 | HASXXX202601X27531 | MOPUA | HAS | NPTAB | $248,938,684 | Associated Construction Services | 2025-08-19 | DELAYED | 96 | 7
27515 | 07 | Rehabilitation of Jawalla Airstrip | HASXXX202601X27515 | MOPUA | HAS | NPTAB | $235,125,965 | Sheriff Construction Inc. | 2025-04-11 | DELAYED | 60 | 7
27359 | 08 | Hinterland Water Supply – Red Creek Kamana | GWIXXX202601X27359 | MOPUA | GWI | NPTAB | $44,600,000 | Alvin Chowramootoo Construction Services | 2026-04-30 | DELAYED | 10 | 0
27476 | 04 | Docking and Rehabilitation of vessel lot 1- ML Thompson | MARADXX202601X27476 | MOPUA | MARAD | NPTAB | $33,203,353 | Guyana Port Inc. | 2025-09-01 | DELAYED | 98 | 1
27471 | 04 | Construction & Rehabilitation Works of VIP Section, New and Existing Commercial Buildings | CJIAXX202601X27471 | MOPUA | CJIA | NPTAB | $1,259,265,155 | PD Contracting | 2023-02-28 | DELAYED | 96 | 71
27461 | 05 | Engineering, Procurement and Construction for Infrastructure Development Projects Phase 2 – Lot 2: Construction of Substations, Transmission Lines, And Reactive Power Reinforcements Within Region No. 5 Of the Demerara Berbice Interconnected System | GPLXXX202601X27461 | MOPUA | GPL | NPTAB | $33,694,921,811 | Kalpataru Projects International Limited | 2026-06-10 | DELAYED | 50.77 | 1
27459 | 04 | Inter Energy - Project Management Consultancy & Owner's Engineering Services. | GPLXXX202601X27459 | MOPUA | GPL | NPTAB | $3,357,900,000 | Inter Energy Holdings UK Limited | 2027-10-08 | DELAYED | 28.21 | 0
27458 | 04 | Engineering, Procurement and Construction (EPC) Services for the Construction of a Building for the Guyana National Control Centre (GNCC) | GPLXXX202601X27458 | MOPUA | GPL | NPTAB | $1,869,621,513 | PowerChina International Group Limited | 2026-03-26 | DELAYED | 97 | 14
27457 | 04 | Engineering, Procurement and Construction for Infrastructure Development Projects Phase 2 – Lot 1 & 3: Construction of Substations, Transmission Lines, And Reactive Power Reinforcements Within Region No. 4 & 6 Of the Demerara Berbice Interconnected System. | GPLXXX202601X27457 | MOPUA | GPL | NPTAB | $57,188,020,580 | PowerChina International Group Limited | 2026-06-10 | DELAYED | 22.6 | 26
27451 | 02 | Procurement of Lithium- Ion Solar Batteries | HECIXX202601X27451 | MOPUA | HECI | NPTAB | $16,804,573 | 2020 FMCG Inc | 2026-02-28 | DELAYED | 0 | 0
27429 | 04 | Automatic Meter Infrastructure - Implementation of smart metering | GWIXXX202601X27429 | MOPUA | GWI | NPTAB | $274,940,000 | Dax Contracting Services | 2026-05-31 | DELAYED | 50 | 0
27420 | 03 | Supply and Installation of 100mm & 150mm Network Mains along Middle Street, Pouderoyen | GWIXXX202601X27420 | MOPUA | GWI | NPTAB | $44,039,250 | DCS Construction Services and General Supplies | 2026-01-27 | DELAYED | 85 | 23
27400 | 06 | Drilling of New Wells – Johanna | GWIXXX202601X27400 | MOPUA | GWI |  | $1,002,251 | Water & Oil Well Services CO. Ltd. |  | DELAYED | 0 | 4
27399 | 06 | Drilling of New Wells – Yakasari | GWIXXX202601X27399 | MOPUA | GWI | NPTAB | $1,002,251 | Water & Oil Well Services CO. Ltd. | 2026-05-12 | DELAYED | 0 | 2
27386 | 04 | Meterinig Programme: Procurement of Water Meters | GWIXXX202601X27386 | MOPUA | GWI | NPTAB | $213,500,000 | Dax Contracting Services | 2026-05-31 | DELAYED | 25 | 0
417 | 08 | Construction of an Administrative Building at the Kato Hydropower Site | HECIXX202510X417 | MOPUA | HECI | NPTAB | $58,401,925 | Hinterland Electrification Co Inc. | 2026-03-31 | DELAYED | 60 | 13