## PSIP Monitoring Form
NO. | AGENCY | 2026 Budget | Method of Procurement | PROCUREMENT TIMELINE (Actual Dates) |  |  |  |  | Tender Status | IMPLEMENTATION | [6 empty] | Remarks
|  |  |  | Tender Advertise | Tender Closed | Date Eval Sent for Approval: |  | Date of Award |  | Contractor / Supplier | Contract Sum | Exp. To Date | Duration months | Start Date | End Date | Status %
[6 empty] | MTB / RTB | NPTAB |  |  |  | 3 Decimal Places |  |  | Example: 1-Jan-2026
Day - Month - Year
34 | MINISTRY OF PUBLIC UTILITIES AND AVIATION
341 | Policy Development & Administration | 5
2513800 | Furniture and Equipment | 5
| 2 Desktop Computers & Accessories | 0.6 | Quotation | [5 empty] | Design
| 2 Desktop Printers | 0.636 | Quotation | [5 empty] | Design
| 2 Laptop Computers | 0.7 | Quotation | [5 empty] | Design
| 4 Office Chairs | 0.424 | Quotation | [5 empty] | Design
| 1 Heavy Duty Photocopier | 2 | Quotation | [5 empty] | Design
| 3 Office Desk | 0.64 | Quotation | [5 empty] | Design
342 | Electricity Service | 50684.9998
2606600 | Lethem Power Company | 185
| General uppgrade of distribution network in Kumu, Moco Moco & St. Ignatius. | 75 | Open Tender | 2026-03-14 | 31/03/26 |  |  |  | Evaluation |  |  |  | 3 | 2026-05-04 | 2026-08-03 |  | Estimated Contract duration
| Installation of new MV switchgear. | 110 | Open Tender | 2026-03-14 | 31/03/26 |  |  |  | Evaluation |  |  |  |  | 2026-05-04 | 2026-08-03 |  | Estimated Contract duration
2606700 | Hinterland Electrification | 500
| Installation of new LV switchgear for power stations at Port Kaituma. | 77 | Open Tender | 2026-02-16 | 17/03/2026 |  |  |  | Evaluation |  |  |  |  | 2026-05-04 | 2026-08-03 |  | Estimated Contract duration
| Installation of 1100kW generator at Mabaruma power station. | 60 | Open Tender | 2026-03-07 | 2026-02-24 |  | 2026-04-14 |  | Evaluation |  |  |  |  | 2026-05-04 | 2026-08-03 |  | Estimated Contract duration
| Installation of 1100kW generator at Kwakwani power station. | 60 | Open Tender | 2026-03-07 | 2026-03-26 |  |  |  | Evaluation |  |  |  |  | 2026-05-04 | 2026-08-03 |  | Estimated Contract duration
| Extension of network to Citrus Groove & 1 Mile old road, Port Kaituma. | 20 | Open Tender | 2026-02-14 | 2026-03-10 |  | 2026-03-25 |  | Awaiting Award |  |  |  |  | 2026-04-17 | 2026-07-16 |  | Estimated Contract duration
| Extension of network to Campbelltown and Airstrip area in Mahdia. | 30 | Open Tender | 2026-02-14 | 2026-03-10 |  | 2026-03-25 |  | Awaiting Award |  |  |  |  | 2026-04-17 | 2026-07-16 |  | Estimated Contract duration
| Continue general upgrade of electricity network at Matthew's Ridge. | 10 | Open Tender | 2026-02-14 | 2026-03-10 |  | 2026-03-25 |  | See Remarks |  |  |  |  | 2026-04-17 | 2026-07-16 |  | To be re-tendered after bids significantly exceeded budget.
| Upgrade of primary circuit to 3-phase from Hosororo to Wauna | 30 | Open Tender | 2026-02-14 | 2026-03-10 |  | 2026-03-25 |  | Awaiting Award |  |  |  |  | 2026-04-17 | 2026-07-16 |  | Estimated Contract duration
| Installation of 500kVA power transformer, and replacement of aged structures in Moruca. | 25 | Open Tender | 2026-03-07 | 2026-03-26 |  |  |  | Evaluation |  |  |  |  | 2026-05-04 | 2026-08-03 |  | Estimated Contract duration
| Installation of two 450kVA generators with related switchgear for Moruca | 55 | Open Tender | 2026-03-07 | 2026-03-26 |  |  |  | Evaluation |  |  |  |  | 2026-05-04 | 2026-08-03 |  | Estimated Contract duration
| Double cab utility trucks for Mahdia, Port Kaituma & Kwakwani.. | 90 | Open Tender | 2026-02-15 | 2026-03-12 |  |  |  | Evaluation |  |  |  |  | 2026-05-04 | 2026-08-03 |  | Estimated Contract duration
| 4x4 All terrain vehicles for HECI engineers. | 30 | Restrictive | 2026-01-02 | 2026-02-11 | 2026-02-11 |  | 2026-03-17 | Award | Beharry Automotive LTD | 13000 | 2026-06-16 | 3 | 2026-03-17 | 2026-06-16
| Payment to B&J Civil Works of retention for defects liability period for the Kato project. | 13 | Nil | [5 empty] | Award
2611300 | Electricity Expansion Programme | 49999.9998
| Rollover: | 45000
| EPC - Double Circuit 69kV River Crossing Underground Transmission Line - HDD between V/Hoop and Kingston Substations | 2812.204 | Sole Source | [5 empty] | Rollover | Capital Edge Partners Inc. | 9643.2 | 5568.948 | 15 | 2026-01-27 | 2027-04-26 | 8.8% | Executing Detailed Engineering Works (Electrical & Civil Designs)
| Substation Expansion for 69kV HDD Submarine Cable in the Demerara River | 1004.3586 | Open Tender | [5 empty] | Evaluation |  | 2583 | 0 |  |  |  |  | Pending NPTAB's Appointment of Eval Committe
| Construction of total 193km/28x 13.8 kV feeders and supply of distribution reinforcement equipment | 2255.5417 | Open Tender | [5 empty] | Rollover | China National Machinery Import and Export Corporation | 7734.3754 | 1160.1564 | 14 | 2026-01-06 | 2027-03-05 | 1.31% | Executing Detailed Engineering Works (Electrical & Civil Designs)
| Supply of 2x 35 MVA, 69/13.8 kV Mobile Substations. | 139.5219 | Open Tender | [5 empty] | Rollover | FIX-IT Depot | 717.6435 | 144.0475 | 12 | 2025-06-04 | 2026-06-25 | 90% | FAT for Mobile Substations to be executed within April 2026.
| Construction of total 42 km/5x 69 kV Lines, four (4) 69/13.8 kV Substations and 17 feeders ~6km per feeder | 9868.0182 | Open Tender | [5 empty] | Rollover | Kalpataru Projects International Limited | 33837.9701 | 9082.44 | 18 | 2026-01-07 | 2027-07-06 | 13.7% | Procurement: 14 items awarded out of 42 tracked. Engineering Design: 54 submitted out of 532 submittals
| Supply and Installation of Advanced Metering Infrastructure (AMI) and 20,000 AMI Meters | 349.156 | Open Tender | [5 empty] | Rollover | FIX-IT Depot | 1436.7292 | 430.5 | 12 | 2025-06-04 | 2026-06-25 | 70% | FAT for AMI Meters & Datacentre to be executed within April 2026.
| Upgrade and Expansion of two (2) 69/13.8 kV Substations | 2236.5491 | Open Tender | [5 empty] | Rollover | Kalpataru Projects International Limited | 9022.6446 | 1737.661 | 18 | 2026-01-07 | 2027-07-06 | 13.7% | Procurement: 14 items awarded out of 42 tracked. Engineering Design: 54 submitted out of 532 submittals
| EPC - IDP Phase 2: Construction of Substations, Transmission Lines and Reactive Power Reinforcements within Reg. Nos. 4 & 6 | 14175.8669 | Open Tender | [5 empty] | Rollover | PowerChina International Group Limited | 57188.0206 | 24564.709 | 12 | 2025-06-10 | 2026-06-10 | 21.08% | Procurement: 14 items awarded out of 42 tracked. Engineering Design: 330 submitted out of 919 submittals Civil Works/Construction: 13% for transmission lines and 0% for substations
| EPC - IDP Phase 2: Construction of Substations, Transmission Lines and Reactive Power Reinforcements within Reg. No. 5 | 7381.2208 | Open Tender | [5 empty] | Rollover | Kalpataru Projects International Limited | 33694.9218 | 9710.104 | 12 | 2025-06-10 | 2026-06-10 | 49.42% | Procurement: 42 items awarded out of 45 tracked. Engineering Design: 256 submitted out of 325 submittals Civil Works/Construction: 10% for transmission lines and 0% for substations
| Construction of 69kV Double Circuit Transmission Lined Between New Georgetown and Sophia Substations | 235.0201 | Sole Source | [5 empty] | Rollover | UCC - KPS JV | 805.896 | 161.1792 | 6 | 2025-12-15 | 2026-06-30 | 20%
| Supply and Installation of 30MW/60MWh Battery Energy Storage Systems | 3347.8619 | Open Tender | [5 empty] | Award |  | 8610 | 0 |  |  |  |  | To conclude Contract Document
| IEH - Project Management Consultancy & Owner's Engineering Services | 816.0413 | Sole Source | [5 empty] | Rollover | Inter Energy Holdings UK Limited | 3497.8125 | 979.388 | 24 | 2025-10-08 | 2027-10-08 | 27.86% | Project Component No. 1: 19.86% Project Component No. 2: 8% Project Component No. 3: 0 %
| ITSS: GTE System's Integration with GNCC and DBIS | 31.3332 | Open Tender | [5 empty] | Rollover | Integrated Telecommunications Services and Solutions Inc. | 214.8877 | 126.0603 | 6 | 2025-10-09 | 2026-04-09 | 70% | Awaiting KPIL to complete works within new substation control buildings.
| SEL: GTE Substation Integration with GNCC and DBIS | 58.2031 | Open Tender | [5 empty] | Award | Schweitzer Engineering Laboratories | 239.4971 | [5 empty] | To conclude Contract Document
| CMC-SIFANG: GTE Substation Integration with GNCC and DBIS | 16.4662 | Open Tender | [5 empty] | Award | China National Machinery Import and Export Corporation | 84.6955 | 16.939 |  |  |  |  | Awaiting Advance Payment to be made to Contractor.
| Power Plant Integration with GNCC | 78.2198 | Sole Source | [5 empty] | Award | Schweitzer Engineering Laboratories | 160.9318 | [5 empty] | To conclude Contract Document
| Land Acquisition | 194.4171 | [8 empty] | 1000 | [5 empty] | Acquisition and Crop compensation ongoing
| New: | 4999.9998
| Repairs to Bartica BESS | 157.828 | Open Tender | [5 empty] | Advertised | [7 empty] | Closing Date: 30th April 2026
| ADSS Fiber Optic Cable Replacement | 17.569 | Open Tender | [5 empty] | See Remarks | [7 empty] | To be executed in-house by the System Control & Operations Department, GPL.
| Sophia - Upgraded to New Sophia - 69 kV - L1/L2 [Construction of a new 69kV T-Line - to increase line caapcity] | 30.722 | Open Tender | [5 empty] | See Remarks | [7 empty] | Incorprated into to EPC+F Project. This project includes for the construction of a new substation at Sophia.
| Phase 2-GNCC/Smart Grid: Preparation of RFP Package | 64.575 | Open Tender | [5 empty] | Design | [7 empty] | Awaiting Approval from NPTAB relative to letter to sole source.
| Leguan Power Plant Switchgear Upgrade | 440.975 | Open Tender | [5 empty] | Design | [7 empty] | To be completed
| Unserved Areas Electrification Programme | 612.1568 | Open Tender | [5 empty] | Design | [7 empty] | Pending NPTAB's Approval of Tender Document
| Leguan and Wakenaam 13.8 kV Interconnection | 904.05 | Open Tender | [5 empty] | Advertised | [7 empty] | Closing Date: 30th April 2026
| Engineering, Procurement and Construction (EPC) Services for the Upgrade of 13.8kV Switchgears at DP2 and DP3 and Tie Lines between stations. | 2772.124 | Open Tender | [5 empty] | Design | [7 empty] | Awaiting NPTAB's Approval of Tender Document for Publishing
343 | Water Services | 10125
2802100 | Hinterland Water Supply | 1500 | [8 empty] | 294.1227
H-001 | Procurement of Photovoltaic systems, electromechanical equipment, pipes, fittings, spares and accessories for new water supply systems | 200 | Open Tender | 2026-01-20 | 2026-02-17 |  |  |  | Evaluation | [7 empty] | Awaiting NPTAB award.
| Supply and delivery of Wellmaster Flexible Rising Mains |  | Sole Source | 2026-02-24 | 2026-03-17 |  |  | 2026-03-31 | Award | Angus Flexible Pipelines | 52.682
H-002 | Procurement of Well Drilling materials to facilitate drilling of wells in 2026 | 40 | Open Tender | [13 empty] | Procurement ongoing
| Supply and delivery of PVC Well casings |  | Sole Source | 2026-03-09 | 2026-03-23 |  |  | 2026-03-31 | Award | Boode b.v | 17.8397 | [5 empty] | Contract signed and awaitng delivery.
PO-3498 | Supply and delivery of 4'' Hammer with 4.5'' Button Bits |  | Quotation | 2026-02-25 | 2026-03-06 |  |  | 2026-03-06 | Award | R. Kissoon Contracting Services | 5.471 | [5 empty] | Awaiting delivery
PO-3497 | Supply and delivery of Bentonite-Quick Gel |  | Quotation | 2026-02-25 | 2026-03-06 |  |  | 2026-03-06 | Award | A. Ahmad Hydraulics | 2.28 | [5 empty] | Awaiting delivery
H-003 | Upgrade of Matthew's Ridge Water Supply System | 20 | Sole Source | na | na |  |  |  | Award | RDC 1 | [6 empty] | MOU signed with RDC 1 , Payment in proecess
H-004 | Rehabilitation works on Port Kaituma Water Supply System | 15 | Sole Source | na | na |  |  |  | Award | RDC 1 | [6 empty] | MOU signed with RDC 1 , Payment in proecess
H-005 | Rehabilitation and upgrade of Mabaruma Pump Stations | 60 | Open Tender | 2026-03-01 | 2026-03-25 |  |  |  | Evaluation | [7 empty] | Evaluation ongoing at NPTAB
H-006 | Installation of Hybrid PV Battery Systems in Para, Waramuri, Baramita (2), Arakaka 5 Miles, Kwebanna, Jawalla, Isseneru, other communituies | 160 | Open Tender | 2026-01-06 | 2026-02-03 |  |  |  | Evaluation | [7 empty] | Evaluation ongoing at NPTAB
H-007 | Installation of elevated trestle in Kangaruma | 6 | Sole Source | na | na |  |  |  | Award | Joshi Construction | [6 empty] | Completed
H-008 | Upgrade of Water Supply System at Wayaleng, Upper Mazaruni, Region 7 | 22 | Open Tender | 2026-01-20 | 2026-02-17 |  |  | 2026-03-03 | Award | Fazam Future Builders | 19.11 | [5 empty] | Contract being finalized
H-009 | Drilling of well in Mahdia, Rehabilitation of Salbora Catchment,transmission & Discharge, Region 8 | 47 | Open Tender | 2026-03-01 | 2026-03-25 |  |  |  | Evaluation | [7 empty] | Evaluation ongoing at NPTAB
H-010 | Drilling of well in Paramakatoi, Region 8 | 35 | Open Tender | 2026-01-20 | 2026-02-17 |  |  | 2026-03-03 | Award | Expert Builders and Supplies Contrcators | 32.41 | [5 empty] | Contract being finalized
H-011 | Installation of Water supply system in section Micobie | 33 | Open Tender | 2026-01-20 | 2026-02-17 |  |  | 2026-03-03 | Award | Monarch Investment | 34.69 | [5 empty] | Project is foe drilling of well at Waramadong; currently being evaluated at NPTAB. Contract being finalized .
H-012 | Construction of new water supply systems in Hobodeiah, Red Hill, Kariako, Warapoka | 100 | Open Tender | [13 empty] | Evaluation ongoing at NPTAB
| Drilling of Potable Wells at Warapoka and Kariako, Region # 1 |  | Open Tender | 2026-01-20 | 2026-02-17 |  |  | 2026-03-03 | Award | NP Contracting & Transportation Services | 46.94 | [5 empty] | Contract being finalized
| Drilling of Potable Wells at Red Hill and Hobodiah Region # 1 |  | Open Tender | 2026-01-20 | 2026-02-17 |  |  | 2026-03-03 | Award | Monarch Investment | 53.54 | [5 empty] | Contract being finalized
H-013 | Construction of Office buildings in Mahdia & Paramakatoi | 67 | Open Tender | [5 empty] | Advertised | [7 empty] | To be tendered
H-014 | Procurement of ATVs and 4x4 vehicles | 20 | [6 empty] | Evaluation
| Supply and delivery of ATVs |  | Quotation | 2026-01-13 | 2026-03-17 |  |  | 2026-03-31 | Award | B&M Trading Enterprise | 8.25 |  |  | 2026-04-13 | 2026-05-12 |  | Order placed, awaiting delivery
| Supply and delivery of Motor Cycles |  | Quotation | 2026-03-19 | 2026-03-26 |  |  | 2026-03-31 | Award | Marics & Company Ltd | 1.01 |  |  | 2026-04-13 | 2026-05-12 |  | Order placed, awaiting delivery
H-015 | Project Administration and Institutional Strengthing | 60 | Open Tender | na | na |  |  |  | Evaluation | [7 empty] | Ongoing ; COWs and Village Councils and Training of CSOs and Hinterland staff
H-016 | Installation of new water system Maloca Nova, Maruranau (Southern Cluster and Eastern Cluster), Katoka, Kumu (Highway Cluster), Yupukari (El Dorado cluster), Moco Moco Settlement, Shea Village (Western Section), Toka Village ( Western Section), Meriwau | 245 | Open Tender | 2026-01-06 | 2026-02-03 |  |  |  | Evaluation | [7 empty] | Evaluation ongoing at NPTAB
H-017 | Drilling of well in Campbelltown, Region 8 | 25 | Sole Source | 2026-03-25 | 2026-03-27 |  |  | 2026-03-30 | Award | Fabra Enterprise | 19.9 | [5 empty] | Contract being finalized
H-018 | Installation of Gravity feed water supply system in Kato, Region 8 | 45 | Open Tender | 2026-01-20 | 2026-02-17 |  |  |  | Evaluation | [7 empty] | Evaluation ongoing at NPTAB
H-019 | Construction of new water supply systems in Bethany (Supenaam Creek), Sand Hills, Kimbia, Ebini, Hururu, Siparuta, Orealla, Moraikobai (Lower), Mashabo | 300 | Open Tender | 2026-01-20 | 2026-02-17 |  |  |  | Evaluation | [7 empty] | Evaluation ongoing at NPTAB
2802200 | Coastal Water Supply | 6445 | [8 empty] | 4904.9308
Rollover:
C-001 | Construction of WTP - Hope | 445 | Open Tender | [5 empty] | Award
| Construction of Surface Water Treatment Plant at Hope, ECD - Lot 1 | 445 | Public Tender | Yes | Yes |  |  | 2024-12-27 | Award | Sigma Engineers Ltd. Inc. | 3057.376 | 912.216 | 18 | 2025-05-12 | 2026-11-12 | 20 | Project progressing as per contract
| Construction of Surface Water Treatment Plant at Hope, ECD - Lot 2 |  | Public Tender | Yes | Yes |  |  | 2024-12-23 | Award | S. Jagmohan Construction and General Supplies. Inc. | 547.5 | 73.88 | 15 | 2026-01-26 | 2027-04-26 | 10 | Project progressing as per contract
New
C-002 | Non Revenue Water programs | 200 | Open Tender | [5 empty] | Design
| Trench Crossing Repairs at Free and Easy to Schoonard, West Bank Demerara, Region No. 3 |  | Quotation | 2026-04-01 | 2026-04-16 |  |  |  | Advertised
| Modification of Distribution Piping System in Region #3 |  | Quotation | 2026-04-01 | 2026-04-16 |  |  |  | Advertised
| Installation of Valve, Flowmeter and Chambers at Nismes to Free and Easy |  | Quotation | 2026-04-01 | 2026-04-16
C-003 | Transmission and Distributions - Hope | 1000 | Open Tender | [5 empty] | Design
| Installation of Transmission Network from Cove & John to Cane Grove, East Coast Demerara, Region 4 (Lot 1: Proposed Water Treatment Plant to Hope Canal) |  | Open Tender | 2025-10-06 | 2025-11-06 |  | 2025-11-20 | 2026-03-30 | Award | Amic General Contracting Services | 70.2064 | 20.0516 | 4 | 2026-03-05 | 2026-07-05 | 5 | Contractor mobilising
| Installation of Transmission Network from Cove & John to Cane Grove, East Coast Demerara, Region no. 4 (Lot 2: Victoria to Hope Estates Road) |  | Open Tender | 2025-10-06 | 2025-11-06 |  | 2025-11-20 | 2026-03-30 | Award | Zeebo & Sons Construction | 45.6984 |  | 4 | 2026-03-05 | 2026-07-05 | 5 | Contractor mobilising
| Installation of Transmission Network from Cove & John to Cane Grove, East Coast Demerara, Region No. 4 (Lot 3: Hope Canal to Old & New Road Intersection) |  | Open Tender | 2025-10-06 | 2025-11-06 |  | 2025-11-20 | 2026-03-30 | Award | Dave Construction & Supply & Establishment | 125.0802 | 31.2701 | 4 | 2026-03-05 | 2026-07-05 | 5 | Contractor mobilising
| Installation of Transmission Network from Cove & John to Cane Grove, East Coast Demerara, Region No. 4 (Lot 4: Old & New Road Intersection to Cambridge) |  | Open Tender | 2025-10-06 | 2025-11-06 |  | 2025-11-20 | 2026-03-30 | Award | Guybiz Establishment | 252.0364 | 63.0091 | 4 | 2026-03-05 | 2026-07-05 | 5 | Contractor mobilising
| Installation of Transmission Network from Cove & John to Cane Grove, East Coast Demerara, Region No. 4. (Lot 5: Cambridge to Vereeniging |  | Open Tender | 2025-10-06 | 2025-11-06 |  | 2025-11-20 | 2026-03-30 | Award | Compass Industrial Sevices | 144.0835 | [5 empty] | Contract awarded
| Installation of Transmission Network from Cove & John to Cane Grove, East Coast Demerara, Region No. 4. (Lot 6: Vereeniging to Cane Grove) |  | Open Tender | 2025-10-06 | 2025-11-06 |  | 2025-11-20 | 2026-03-30 | Award | DJ General Construction And Supplies | 59.5447 | 14.8862 | 4 | 2026-03-05 | 2026-07-05 | 5 | Contractor mobilising
| Supply and Installation of 200mm Transmission & 100mm Distribution Mains along Naamryck-Consservancy Road, Parika |  | Open Tender | 2026-04-01 | 2026-04-30 |  |  |  | Advertised | [7 empty] | Bids opening 30 April 2026
| Supply and Installation of 250mm Transmission Mains at Tuschen, Region # 3 |  | Open Tender | 2026-04-01 | 2026-04-30 |  |  |  | Advertised | [7 empty] | Bids opening 30 April 2026
C-004 | Gravity Filters -Diamond, Uitvlugt | 200 | Open Tender | [5 empty] | Design
C-005 | Technical Support Consultancy Services for Coastal Water Treatment Plants | 75 | Open Tender | [5 empty] | Design
C-006 | Surface WTP (Stewartville) | 250 | Open Tender | [5 empty] | Design
C-007 | Surface WTP (La Bonne Intention) | 250 | Open Tender | [5 empty] | Design
C-008 | Inline Filters -Providence, De Hoop, Mon Repos, Calcutta, Agricola, Coldingen and Annandale | 700 | Open Tender | [5 empty] | Design
C-009 | Installation of Water Meters and Boxes: | 100 | Sole Source
GWI 2026/CPA 576 |  |  | Sole Source | 2026-02-18 | 2026-03-04 |  |  |  | Award | Caimraj Goolab | 5
GWI 2026/CPA 574 |  |  | Sole Source | 2026-02-18 | 2026-03-04 |  |  |  | Award | Virjanand Ramlal | 5
GWI 2026/CPA 416 |  |  | Sole Source | 2026-01-01 | 2026-01-29 |  |  |  | Award | Besham Deolall | 5 |  |  | 2026-01-22 | 2026-04-22
GWI 2026/CPA 543 |  |  | Sole Source | 2026-03-03 | 2026-03-10 |  |  |  | Award | Besham Deolall | 5 |  |  | 2026-03-17 | 2026-07-17
|  |  | Sole Source | 2026-03-03 | 2026-03-10 |  |  |  | Award | Keyon Boyce | 5
GWI 2026/CPA 567 |  |  | Sole Source | 2026-02-18 | 2026-03-04 |  |  |  | Award | Ravindra Deonaraine | 5 |  |  | 2026-03-17 | 2026-07-17
GWI 2026/CPA 546 |  |  | Sole Source | 2026-02-18 | 2026-03-04 |  |  |  | Award | Osprey Investment Inc. | 5 |  |  | 2026-03-17 | 2026-07-17
GWI 2026/CPA 544 |  |  | Sole Source | 2026-03-02 | 2026-03-12 |  |  |  | Award | Romel Birkett | 5 |  |  | 2026-03-17 | 2026-07-17
GWI 2026/CPA 575 |  |  | Sole Source | 2026-03-02 | 2026-03-12 |  |  |  | Award | AAA Rahman Inc. | 5
GWI 2026/CPA 452 |  |  | Sole Source | 2026-02-18 | 2026-03-04 |  |  |  | Award | Azad Rahamat | 5 |  |  | 2026-02-03 | 2026-05-03
GWI 2026/CPA 450 |  |  | Sole Source | 2026-02-18 | 2026-03-04 |  |  |  | Award | Roderic Carrington | 5 |  |  | 2026-02-03 | 2026-05-03
GWI 2026/CPA 449 |  |  | Sole Source | 2026-02-18 | 2026-03-04 |  |  |  | Award | Ravindra Deonaraine | 5 |  |  | 2026-02-03 | 2026-05-03
GWI 2026/CPA 483 |  |  | Sole Source | 2026-02-18 | 2026-03-04 |  |  |  | Award | Ptolemy Hamlin | 5 |  |  | 2026-02-03 | 2026-05-03
GWI 2026/CPA 547 |  |  | Sole Source | 2026-02-18 | 2026-03-04 |  |  |  | Award | Razia Sanicharra | 5 |  |  | 2026-03-17 | 2026-07-17
GWI 2026/CPA 568 |  |  | Sole Source | 2026-02-18 | 2026-03-04 |  |  |  | Award | Kumar Narine | 5 |  |  | 2026-03-17 | 2026-07-17
GWI 2026/CPA 545 |  |  | Sole Source | 2026-02-18 | 2026-03-04 |  |  |  | Award | N & S Contruction | 5 |  |  | 2026-03-17 | 2026-07-17
GWI 2026/CPA 451 |  |  | Sole Source | 2026-02-18 | 2026-03-04 |  |  |  | Award | Rawl Carryl |  |  |  | 2026-02-03 | 2026-05-03
C-010 | Procurement of service connection materials LOT 2: Saddles | 100 | Open Tender | [5 empty] | Design
| Supply and delivery of 4' and 6" Ferrule Straps |  | Sole Source | 2025-11-17 | 2025-11-21 | 2025-11-24 |  | 2025-11-24 | Award | Atlantic Plastic Ltd. | 14.6172 |  |  | 2026-03-16 | 2026-06-09 |  | Contract signed and advance payment made.
C-011 | Procurement of service connection materials LOT 3: Polyhose | 50 | Open Tender | [5 empty] | Design
| Supply and delivery of Poly Hose |  | Sole Source | 2026-02-16 | 2026-02-23 | 2026-03-02 |  | 2026-03-02 | Award | Gafsons Industries Limited | 18.48 |  |  | 2026-03-09 | 2026-06-29 | 30% | Phase delivery
C-012 | Procurement of service connection materials LOT 4: Poly fittings | 100 | Open Tender | [5 empty] | Design
C-013 | Procurement of service connection materials LOT 5: Stop Cock | 100 | Open Tender | [5 empty] | Design
| Supply and delivery of stop Cock Brass valves |  | Sole Source | 2025-11-12 | 2025-11-18 | 2025-11-24 |  | 2025-11-24 | Award | Aalbert Integrated Piping Systems Ltd. | 19.2997 |  |  | 2026-03-16 | 2026-06-09 |  | Contract signed and advance payment made.
C-014 | Well drilling materials | 320 | Open Tender | [5 empty] | Design
PO-2534 | Procurement of Stainless Steel Well Drilling Materials |  | Sole Source | [5 empty] | Award | Johnsons Screens | 150.8459 |  |  | 2026-04-01 | 2026-07-31 |  | Contract signed and supplier is manufacturing goods
PO-2532 | Procurement of Critical PVC Well Drilling Materials |  | Sole Source | [5 empty] | Award | Boode B.V | 134.1447 |  |  | 2026-04-01 | 2026-07-31 |  | Contract signed and supplier is manufacturing goods
PO-3705 | Supply and delivery of Mild Steel Conductors Casings 24''x1/4'' |  | Quotation | 2026-02-28 | 2026-03-06 |  |  |  | Award | Compass Industrial Services | 9.759 |  |  | 2026-03-13 | 2026-03-20 | 100% | Delivery completed
PO-3707 | Supply and delivery of Mild Steel Conductors Casings 24''x1/4'' |  | Quotation | 2026-03-17 | 2026-03-24 |  |  |  | Award | Compass Industrial Services | 9.759 |  |  | 2026-03-31 | 2026-04-14 | 100% | Delivery completed
C-015 | Drilling of New Well - Betterhope | 150 | Open Tender | 2026-02-28 | 2026-03-31 |  |  |  | Evaluation | [7 empty] | Bids closed on March 31, 2026. Currently under evalaution.
C-016 | Drilling of New Well - Timerhi #5 | 150 | Open Tender | 2026-02-28 | 2026-03-31 |  |  |  | Evaluation | [7 empty] | Bids closed on March 31, 2026. Currently under evalaution.
C-017 | Drilling of New Well - Grove | 150 | Open Tender | 2026-02-28 | 2026-03-31 |  |  |  | Evaluation | [7 empty] | Bids closed on March 31, 2026. Currently under evalaution.
C-018 | Drilling of New Well - Port Mourant | 150 | Open Tender | 2026-02-28 | 2026-03-31 |  |  |  | Evaluation | [7 empty] | Bids closed on March 31, 2026. Currently under evalaution.
C-019 | Drilling of New Well - Vergenoegen | 150 | Open Tender | 2026-02-28 | 2026-03-31 |  |  |  | Evaluation | [7 empty] | Bids closed on March 31, 2026. Currently under evalaution.
C-020 | Procurement of Electromechanical equipment for rehabilitation to production facilities | 400 | Open Tender | 2026-02-28 | 2026-03-31 |  |  |  | Evaluation | [7 empty] | Bids closed on March 31, 2026. Currently under evalaution.
| Supply and delivery of Wellmaster Flexible Rising Mains |  | Sole Source | 2026-02-24 | 2026-03-17 |  |  | 2026-03-31 | Award | Angus Flebile Pipelines | 134.1261
C-021 | Extension of transmission and distribution systems to unserved areas: | 200 | Open Tender | [5 empty] | Design
| First Time Access at Airy Hall, Middle Walk (North to South), Mahaica, Region # 5 |  | Open Tender | 2026-03-29 | 2026-04-24 |  |  |  | Advertised
| First Time Access at Nigg & Hampshire Villages, Region # 6 |  | Open Tender | 2026-03-29 | 2026-04-24 |  |  |  | Advertised
| First Time Access at Catherine Middle Walk (North of Public Road), Mahaica, Region # 5 |  | Open Tender | 2026-03-29 | 2026-04-24 |  |  |  | Advertised
| First Time Access at Brothers' Village, Region # 6 |  | Open Tender | 2026-03-29 | 2026-04-24 |  |  |  | Advertised
| First Time Access at Gilbrator Village, Region # 56 |  | Open Tender | 2026-03-26 | 2026-04-23 |  |  |  | Advertised
| First Time Access at Mibicuri Village, Region # 6 |  | Open Tender | 2026-03-26 | 2026-04-23 |  |  |  | Advertised
| Supply and Installation of PVC Distribution Mains at 3 Mile Access Road, Bartica, Region No.7 |  | Open Tender
| Supply and Installation of PVC Distribution Mains at Black’s Road, Bartica, Region No.7 |  | Open Tender
| Supply and Installation of PVC Distribution Mains at Fowl Cock Road, Bartica, Region No.7 |  | Open Tender
C-022 | Road Reinstatement | 100 | Open Tender | [5 empty] | Design
| Reinstatement works at Broad Street, Saffon Street, West Ruimvedt, Benn Street, Norton & Cemetery Road, Itunii Street, South & Oronque Street, Hostel Street, Lance Gibbs Street, Main Street, Haley Street, Avenue of REpublic and Church Street |  | Sole Source | 2026-03-30 | 2026-04-06 |  |  | 2026-04-10 | Award | P.E.A.S General Construction & Supplies | 13.6816 |  |  |  |  | 100% | Works completed.
| Reinstatement works at Water Street and Avenue od Republic |  | Sole Source | 2026-02-09 | 2026-02-16 |  |  | 2026-02-18 | Award | P.E.A.S General Construction & Supplies | 12.826 |  |  |  |  | 100% | Works completed.
| Reinstatement works at Various Locations within Georgetown |  | Sole Source | 2026-02-02 | 2026-02-06 |  |  | 2026-02-09 | Award | P.E.A.S General Construction & Supplies | 5.866 |  |  |  |  | 100% | Works completed.
C-023 | Advance Digital Transformation (Establishment Operation Control Centre) | 100 | Open Tender | [5 empty] | Design | P.E.A.S General Construction & Supplies
C-024 | Construct 2000 sanitation blocks Phase 2 | 500 | Open Tender | 2026-04-12 | 2026-04-24 |  |  |  | Advertised | [7 empty] | Bids opening on April 24, 2026
C-025 | Project administration | 60 | Open Tender | [5 empty] | Design
2802600 | Urban Sewerage and Water | 2180 | [8 empty] | 2757.0104
Rollover:
U-001 | GWI Head Office | 300 | Open Tender | [5 empty] | Award
U-002 | New Water Supply System - New Filter -Shelter Belt upgrade | 1000 | Open Tender | Yes | Yes |  |  | Yes | award | Sigma Engineer's Ltd. Inc. | 2439.895 | 484.738 | 24 | 2026-03-02 | 2028-03-02 | 2% | Project progressing as per contract
New:
U-003 | Drilling of New Well # Central Ruimveldt | 180 | Open Tender | 2025-10-13 | 2025-11-11 |  | 2025-11-20 | 2025-12-03 | Award | Well Drilling Services Inc. | 214.2849 |  |  | 2026-03-30 | 2026-07-31 |  | Contractor Mobilized at site.
U-004 | Drilling of New Well # Shirley Field Ridley | 150 | Open Tender | 2026-02-28 | 2026-03-31 |  |  |  | Evaluation | [7 empty] | Bids closed on March 31, 2026. Currently under evalaution.
U-005 | Drilling of New Well # Houston | 150 | Open Tender | 2026-02-28 | 2026-03-31 |  |  |  | Evaluation | [7 empty] | Bids closed on March 31, 2026. Currently under evalaution.
U-006 | Sanitation - rehabilitate G/town sewer stations and network | 300 | Open Tender | [5 empty] | Design
| Supply and deivery of Branes Chopper Dry Pit Submericable Pumps with Accessories |  | Sole Source | 2025-11-03 | 2025-11-03 |  |  | 2025-11-19 | Award | JKA Pump | 84.9093 |  |  | 2026-02-27 | 2028-06-30 |  | Contract signed and advance pament made.
| Raising of chambers and Manholes in Alberttown Zones, Georgetown |  | Quotation | 2026-03-20 | 2026-03-27 |  |  |  | Award | Baroque Engineering and Cobstruction Services | 7.1753 |  |  | 2028-04-17 | 2028-06-15 |  | Contract awarded.
| Raising of chambers and Manholes in North and South Cumminngsburg Zones, Georgetown |  | Quotation | 2026-03-20 | 2026-03-27 |  |  |  | Award | Baroque Engineering and Cobstruction Services | 9.4005 |  |  | 2028-04-17 | 2028-06-15 |  | Contract awarded.
| Sewer Modification at Lot 15-15 Norton Streets, Wortmanville, Georgetown |  | Quotation | 2026-03-20 | 2026-03-27 |  |  |  | Award | Statix Construction and General Supplies | 1.3454 |  |  | 2028-04-17 | 2028-06-15 |  | Contract awarded.
U-007 | Waste Water Treatment Plant | 100 | Open Tender | [5 empty] | Design | [7 empty] | Awaiitng the submission of the Technical and Financial Proposals from the shrotlisted consultants. This process is being executed by IDB.
344 | Aviation | 5405.5857
| RFP (EPC + F) for a code 3C airport at Rose Hall (Greenfield Project) | 100 | Open Tender | [5 empty] | Advertised | [7 empty] | We are awaiting Proposals. 9th Ex
| RFP (EPC + F) for a code 4E airport at Lethem (Greenfield Project) | 0 | Open Tender | [5 empty] | Advertised | [7 empty] | We are awaiting Proposals to know cost.
1601100 | Hinterland/Coastal Airstrips | 3999.9997
Rollover:
| Rehabilitation of Kwakwani Airstrip, Region 10 | 6.2235 | Sole Source | [5 empty] | Award | Assoicated Construction Services | 248.9387 | 242.7152 | 5 | 2025-03-19 | 2026-02-28 | 95% | 1) Works substantially completed; 2) Contractor was written on Oct 29 to have corrective and outstanding works completed by Nov. 15, 2025. 3) Internal auditors to conduct physical verification of works during the week of December 28, 2025 before release of final payment. 4) Corrective Works to be undertaken prior to formal opening. 5) Contractor indicated that corrective works have been completed. 6) A joint site visit was done on March 10 to assess standards of corrective works; due to unfavorable weather conditions, this could not have been conducted and was rescheduled to the week of April 12, 2026. 7) Site inspection was done on April 14, 2026 to assess quality of corrective works; more corrective works will have to be undertaken prior to formal reopening.
| Phase 2: Extension of Ekereku Bottom Airstrip, Region 7 | 510.3374 | [6 empty] | Award | Gyana Defence Force in collaboration with MoPW | 734.4162 | 224.0788 | 13 | 2025-11-24 | 2026-12-18 | 1% | 1) Following consultations with GDF at a Ministerial Level, it was decided to extend the length of Ekereku Bottom Airstrip. 2) Mobilization of equipment and personnel on-going; 850 sacks of cement currently stored on site. 3) Project cost increased due to logistical challenges in mobilizing materials. 4) Delays in mobilization due to military action close to Venezuela Border; pieces of equipment are on site and other pieces still to be transported via Sky Van which was down for maintenance. 5) Meeting to discuss project implementation rescheduled due to Ministerial Commitments. New date likely to be within the week of April 12, 2026.
| Rehabilitation of Kaikan Airstrip, Region 7 | 766.1522 | [6 empty] | Award | Gyana Defence Force in collaboration with MoPW | 1044.1761 | 278.0239 | 30 | 2024-12-04 | 2027-06-09 | 1% | 1) Mobilization of Equipment and Personnel ongoing. 2) Adjustments to the initial scope of works made prevent closure and inconvenience to the residents of Kaikan Village; project cost increased. 3) Awaiting public consultation with Minister and Village Reps. prior to commencement of physical works on the runway. 4) Delays in mobilization resulted from military actions close to Venezuela Border; meeting held with GDF to discuss implementation arrangements. 5) Project meeting to discuss implementation arrangements rescheduled due to Ministerial Commitments; new date likely to be within the week of April 12, 2026.
| Lot 3: Supply and Transportation of Materials for Construction of Matthew's Ridge Airstrip Region 1- Supply of Concrete | 492.7493 | Restrictive | [5 empty] | Award | GV Construction Inc. | 985.4985 | 492.7493 | 10 | 2025-06-25 | 2026-04-30 | 50% | 1) Works being executed by Ministry of Public Works' Special Projects Unit in collaboration with Matthew's Ridge Community. 2) Project is 54% completed; concrete works approximately 50% completed. Taxi way completed. 3) Works were protracted due to condition of road during rainy season. 4) Works continue to be delayed due to persistent and infrequent rainfall; Completion date likely for June 30, 2026.
| Lot 1: Rehabilitation of Anna Regina Airstrip, Region 2 | 49.6415 | Restrictive | [5 empty] | Award | Builders Hardware General Supplies and Construction | 194.8593 | 145.2179 | 2.5 | 2026-01-19 | 2026-03-30 | 95% | 1) Works substantially completed. 2) Outstanding works include installation of gate for perimeter fence and placement and compaction of shoulder material.
| Lot 2: Construction of Waiting Facility at Anna Regina Airstrip, Region 2 | 18.5447 | Restrictive | [5 empty] | Award | ICAN Engineering & Construction | 26.4925 | 7.9477 | 4 | 2026-01-19 | 2026-05-19 | 60% | 1) Site visit done with Contractor on January 11. 2) Excavation of foundation and sandfill completed; casting of foundation and 11 columns completed. 3) Casting of floor slab completed. Laying of blocks for exterior walls completed; casting of 7 window lintels completed. 4) Plastering of internal walls completed; casting of handicap ramp completed. Cuttings for plumbing and electrical works on-going. 5) Framing of roof completed; installation of zinc members completed. 6) Contractor indicated difficulties in procuring windows from Gafoors during a site visit conducted on April 10, 2026; the supplier gave a commitment to have the materials supplied during the week of April 12, 2026.
New:
| Rehabilitation of Karasabai Airstrip, Region 9 | 1053.8819 | Comm.Participation | [5 empty] | Award | MoPW's SPU in collaboration with MPUA & Community | 1053.8819 |  | 2.5 | 2026-01-19 | 2026-03-31 | 100% | 1) Works completed. 2) Airstrip commissioned on April 04, 2026 by His Excellency.
| Construction of Parking Apron at Kaieteur Airstrip, Region 8 | 200 | Sole Source | [5 empty] | Award | Guyana Defence Force in collaboration with MPUA |  |  | 5.5 | 2026-03-16 | 2026-08-31 | 44% | 1) Works are being implemented by the Guyana Defence Force in collaboration with the Ministry of Public Utilities & Aviation. 2) Concrete Works approximately 40.5% completed; sections measuring 250ft by 50ft and 108ft by 25ft were cast. 3) Works are protracted due to persistent rainfall. 4) Transportation of cement from Mahdia to Kaieteur utilizing local air service providers have slowed down. This will impact the rate of progress of concrete works.
| Rehabilitation of Monkey Mountain Airstrip, Region 8 | 802.4692 | Comm.Participation | [5 empty] | Award | MoPW's SPU in collaboration with MPUA & Community |  |  | 4 | 2026-04-11 | 2026-08-11 | 1% | 1) Site inspection conducted on April 11, 2026 2) Engineering surveys completed.
| RFP (EPC + F) for a code 3C airport at Rose Hall (Greenfield Project) | 100 | Open Tender | [5 empty] | Advertised | [7 empty] | We are awaiting Proposals. Bids extended for 2 months and will open on June 9, 2026
| RFP (EPC + F) for a code 4E airport at Lethem (Greenfield Project) |  | Open Tender | [5 empty] | Advertised | [7 empty] | We are awaiting Proposals. Bids extended for 2 months and will open on June 9, 2026
1601500 | CJIA Corporation | 505.586
| Rehabilitation of the Runway and Taxiway at CJIA | 500 | Open Tender | [5 empty] | Design | [7 empty] | The revised BOQ was sent on 30th March 2026. This is being finalized. To be advertised in April 2026.
| Procurement & Installation of Wheelchair Lift for the Commercial Building | 5.586 | Sole Source | - | - | - | 31/10/2023 | 15/11/2023 | Award | Total Solutions | 11172000 | 5586000 | 6 | 2024-05-01 | 2024-05-07 | 95% | The contract was awarded in 2023. The equipment is installed but the commissioning is pending the completion of the commercial building.
1602000 | Civil Aviation Authority | 900
| Construction of New Air Traffic Control Tower at Timehri | 800 | Open Tender | [5 empty] | Advertised | [7 empty] | The tender was extended by 1 month because of additional technical information bidders needed. Bids will open on Tuesday May 19th.
| Construction of Centre of Aviation: Civil Aviation Training School + GCAA HQ | 100 | Open Tender | [5 empty] | Design | [7 empty] | Awaiting Policy Direction whether we go with RFP (EPC + F) or we start the project with 100M and budget for additional resources in supplemental. Note: We have a design, but this will need updating. Depending on the policy advise we will know how to proceed.
345 | Maritime Administration | 6475
1403900 | Dredging | 6255
| Dredging of Demerara River and main ships' channel | 6255 | Open Tender | [5 empty] | See Remarks | [7 empty] | Awaitng Policy Direction
2607000 | Navigational Aids | 220
| Supply and Delivery of Tide Monitoring (Radar and Pressure) Systems and Accessories | 75 | Open Tender | [5 empty] | Advertised | [7 empty] | Tender Document resubmitted to NPTAB on Friday, April 10, 20206 after being returned for clarification on Technical Specifications.
| Acquisition of Spares (Aids to Navigation) | 70 | Open Tender | [5 empty] | Advertised | [7 empty] | Tender Document resubmitted to NPTAB on Friday, April 10, 20206 after being returned for clarification on Technical Specifications.
| Supply and Delivery of MET Ocean Buoy and Accessories | 75 | Open Tender | [5 empty] | Advertised | [7 empty] | Tender Document resubmitted to NPTAB on Friday, April 10, 20206 after being returned for clarification on Technical Specifications.
Summary:
| Rollover | 40300.4734
| Design | 8699.8308
| Advertised | 2848.878
| Evaluation | 4143.3586
| Awaiting Award | 80
| Award | 9975.3366

## UKEF - 342
NO. | AGENCY | 2026 Budget | Method of Procurement | PROCUREMENT TIMELINE (Actual Dates) |  |  |  |  | Tender Status | IMPLEMENTATION | [6 empty] | Remarks
|  |  |  | Tender Advertise | Tender Closed | Date Eval Sent for Approval: |  | Date of Award |  | Contractor / Supplier | Contract Sum | Exp. To Date | Duration months | Start Date | End Date | Status %
[6 empty] | MTB / RTB | NPTAB |  |  |  | 3 Decimal Places |  |  | Example: 1-Jan-2026
Day - Month - Year
34 | Ministry of Public Utilities & Aviation
342 | Electricity Services
2611300 | Electricity Expansion Programme | 16179.6
| EPC Financing for GPL - UCC $500M | 15637.5 | Open Tender | [5 empty] | Design
| Supervision - 4mths at US$650k | 542.1 | Open Tender | [5 empty] | Design
Summary:
| Rollover | 0
| Design | 0
| Advertised | 0
| Evaluation | 0
| Awaiting Award | 0
| Award | 0

## IDB -343
NO. | AGENCY | 2026 Budget | Method of Procurement | PROCUREMENT TIMELINE (Actual Dates) |  |  |  |  | Tender Status | IMPLEMENTATION | [6 empty] | Remarks
|  |  |  | Tender Advertise | Tender Closed | Date Eval Sent for Approval: |  | Date of Award |  | Contractor / Supplier | Contract Sum | Exp. To Date | Duration months | Start Date | End Date | Status %
[6 empty] | MTB / RTB | NPTAB |  |  |  | 3 Decimal Places |  |  | Example: 1-Jan-2026
Day - Month - Year
34 | Ministry of Public Utilities & Aviation
343 | Water Service Expansion and Management
1601800 | Climate Resilient Water Infrastructure Improvement Project | 4500
1 | Procurement of Plant: Design, Supply, Installation & Commissioning of Surface Water Treatment Facilities at Diamond, East Bank Demerara, Region No. 4 |  | ICB | 2025-11-03 | 2025-12-30 | - | - | Expected | Under evaluation | [7 empty] | Five bids were submitted and are currently under evaluation. The evaluation report is expected to be submitted by February 26, 2026.
1.1 | Construction of Surface Water Treatment Plant | 3500
1.2 | Construction of surface water intake for abstraction of surface water from the EDWC | 100
1.3 | Construction of solar energy generation system | 100
2 | Procurement of materials for transmission mains | 100 | ICB | Expected | Expected |  |  | Expected
3 | Development and Implementation of NRW action plan (Individual Consultant) | 5 | 3CV | Expected | Expected |  |  | Expected
4 | Implementation of NRW action plan (advertisments, stakeholder engagements etc.) | 6 | 3CV | Expected | Expected |  |  | Expected
5 | Procurement of leakage equipment, NRW related materials etc. | 40 | ICB | Expected | Expected |  |  | Expected
6 | Network modification and installation of DMAs | 38 | ICB | Expected | Expected |  |  | Expected
7 | Procurement of smart meters | 300 | ICB | Expected | Expected |  |  | Expected
8 | Implementation of digital transformation action plan | 51 | OCBS | Expected | Expected |  |  | Expected
9 | Upgrade of commercial and financial management system (billing software) | 90 | OCBS | Expected | Expected |  |  | Expected
10 | Project Management | 40 | Shopping | Expected | Expected |  |  | Expected
11 | Consultancy services for Supervision of the Works - Design Review and Supervision of the Construction of a Water Treatment Plant at Great Diamond (Block 3), East Bank Demerara | 105 | QCBS | 2025-09-28 | 2025-10-14 | - | - | Expected | Under evaluation | [7 empty] | Eleven expressions of interest were received. These are under evaluation for shorting of firms after which the request for proposals (RFP) will be sent to the shortlisted firms for their technical and financial proposals.
12 | Project Administration | 25 | CQS | Expected | Expected
Summary:
| Rollover | 0
| Design | 0
| Advertised | 0
| Evaluation | 0
| Awaiting Award | 0
| Award | 0

## CDB - 343
NO. | AGENCY | 2026 Budget | Method of Procurement | PROCUREMENT TIMELINE (Actual Dates) |  |  |  |  | Tender Status | IMPLEMENTATION | [6 empty] | Remarks
|  |  |  | Tender Advertise | Tender Closed | Date Eval Sent for Approval: |  | Date of Award |  | Contractor / Supplier | Contract Sum | Exp. To Date | Duration months | Start Date | End Date | Status %
[6 empty] | MTB / RTB | NPTAB |  |  |  | 3 Decimal Places |  |  | Example: 1-Jan-2025
Day - Month - Year
Agency No. 34 | Name of Agency - Ministry of Public Utilities & Aviation
Programme No.343 | Programme Title: Water Supply Improvement Project
GOG funded (counterpart resources)
| Construction of Water Treatment Plant at Leguan and Wakenaam | 441 | ICB | Yes | Yes |  |  | Yes | Award | Sigma Engineers Ltd and Hebei Wansheng Environmental Protection Engineering Co. Ltd JV | 1486.448 | 887.447 | 18 | 2025-11-13 | 2026-06-13 | 60 | Construction is progressing as per contract
| Project Administration | 46 | CQS | Yes | Yes |  |  | Yes | Award | Candice Ramessar and Devika Sam | 32.55 | - | 21 |  |  | 0 | Contracts to be signed for the Social and Gender Safeguard Specialist and Environmental Specialist in Apr. 2026
CDB/EIB funded
| Construction of WTPs | 912 | ICB | Yes | Yes |  |  | Yes | Award | Action Construction Equipment Ltd. And Phoenix Private Projects Ltd. | 2767.967 | 1595.43 | 18 | 2025-11-13 | 2026-06-13 | 46 | Construction is progressing as per contract
| Drilling of Wells: | 834
| Lot 1 | 834 | ICB | Yes | Yes |  |  | Yes | Award | S.Jagmohan Construction and General Supplies Inc. | 371.519 | 92.88 | 6 | 2026-03-19 | 2026-09-19 | 0 | Contract signed and commencement order issued.
CPA 562 | Lot 2 |  | ICB | Yes | Yes |  |  | Yes | Award | ACE-Hugel JV | 569.088 |  | 6 |  |  | 0 | Contract signed.
| Transmission Mains | 2519 | ICB | Expected | Expected |  |  | Expected | Expected | [7 empty] | Bids to be advertised in April, 2026
| Consultancy services for supervision of the works | 400 | QCBS | Yes | Yes |  |  | Yes | Yes | EXP Services Inc. in association with CB Associates Inc. | 874.45 | 418.03 | 26 | 2024-12-06 | 2027-03-06 | 54 | Construction is progressing as per contract
| Consultant for NRW reduction | 20 | QCBS | Expected | Expected |  |  | Expected | Expected
| Procurement of vehicles for NRW works | 49 | LB | Expected | Expected |  |  | Expected | Expected
| Procurement of leakage equipment and materials | 162 | LB | Expected | Expected |  |  | Expected | Expected
| Project Administration | 25 | CQS | Expected | Expected |  |  | Expected | Expected
| NRW works within the project areas | 79 | LB | Expected | Expected |  |  | Expected | Expected
[11 empty] | 6102.022 | 2993.787